## Slide 1: Manage your (survey) contractor
It will save you headaches in the long run
IRWA Conference | Portland, Oregon
March 20, 2019
Notes: Todd – Welcome to Manage your survey contractor*

## Slide 2: WELCOME
Welcome - Todd
  Survey Committee
  During the presentation, text any questions to: 281-853-5260
Safety Moment - Todd
  How to be safe while traveling
Objectives - Mike
  The importance of prequalifying your contractor
  The importance of providing an accurate RFP to your potential contractor
  The importance of successfully managing the contractor relationship
Notes: Todd – Room directions (if not done by host) and a relevant safety moment.
- Mention Survey Committee and what it does.
Text questions to….
Safety Moment
Objectives – Mike
As surveyors we want to have a short presentation and open discussion about
- how you can get the best from your survey contractor,
how to better communicate your needs at the beginning of a project to ensure you get the deliverables you expect and the service you deserve,
- highlight some areas where you might be seeing problem areas and ways to mitigate that in the future.

## Slide 3: Introduction
Todd Rakstad PLS, SR/WA
  Survey Manager
  Salt River Project, Phoenix, AZ
    AZ, CO, NV, SD & UT
James M. (Mike) Hart, LS, CFedS
  Survey Manager
  Cardno, Phoenix, AZ
    AR, AZ, CA, CO, ND, NE, NM, NV, OK, OR, SD, UT
Terry L. Rowe, RPLS, LSLS, PMP
  Director, GIS and Mapping
  Percheron Professional Services LLC, Katy, TX
    AL, AR, AZ, CA, CO, KS, KY, MD, MS, MT, NC, ND, NE, NV, NY, OK, PA, SD, TN, TX, UT, VA, WI, WV, WY
Notes:   Everyone introduces themselves
  I am…
  I work for…
  I have been surveying for ___ years and talk a little bit about your experience…
  States you are licensed in…
  Most interesting project management experience… (Something for people to remember you by).
  GM, I am Terry Rowe and I work for Percheron Professional Services. My current position is the Director of GIS and Mapping, but I spend most of my time working with the surveying group. I have been surveying over 35 years starting as a rodman on a crew in MD and working my way through the ranks. I am registered in 25 states and also have my Project Management Professional certification. My most interesting project management experience was when I worked with AECOM in Libya on several infrastructure projects. My exit was on a ferry leaving the Port of Tripoli as the rebels were moving in to take out Ghadaffi.
  Let’s get into the meat of the discussion*

## Slide 4: PREQUALIFYING YOUR SURVEYOR

## Slide 5: PREqualifying your surveyor
Confirm the Contractor is licensed in the State the work is located.
  Is the surveyor licensed and registered?
  Is the company registered?
Confirm Contractor Meets Your Safety Requirements.
  Use your inhouse Health, Safety, Security, and Environmental (HSSE) group, if available, to ensure compliance.
  Is ISNetworld, OSHA10, OSHA30, or other training required?
  Ask for Contractor Safety Point of Contact information
  Ask for Copies of relevant certificates and other documentation
  Drone Licensing – FAA Part 107, Class 3 Medical Certification
  Include any requirements in Request for Proposal

## Slide 6: Why state licensure?
State Licensure - Terry
  Requirements
    Each state has laws and rules that regulate the surveying profession to protect the public.
    Some of these rules are very broad and include items such as GIS exhibits, maps, or other items which show property lines or might create the idea in the public’s mind that they are looking at a surveyed work product.
    States have requirements for the company which must be followed.
  Why you should confirm licensure?
    Limit delays on the project
    Ensure the deliverables meet State standards
  Are these services regulated?
    LiDAR, Aerial Mapping, Drone Mapping, GIS
  For example…
Notes: Making sure your surveyor can be as simple as a statement in a Request for Proposal or Bid with a statement stating such. Maybe

## Slide 7: Why state licensure?
State Licensure - Terry
  Kansas - (1) "Professional surveying" or "practice of professional surveying" means providing, or offering to provide, professional surveying services including the following:
    Common technical services, as defined in subsection (g); using such sciences as mathematics, geodesy and photogrammetry; and involving
    the making of geometric measurements and gathering related information pertaining to the physical or legal features of the earth, improvements on the earth, the space above, on or below the earth and providing, utilizing or developing the same into survey products such as graphics, data, maps, plans, reports, descriptions or projects.
    Professional surveying services also include planning, mapping, assembling and interpreting gathered measurements and information related to any one or more of the following:
      (A) Determining by measurement the configuration or contour of the earth's surface or the position of fixed objects thereon;
      (B) determining by performing geodetic surveys the size and shape of the earth or the position of any point on the earth;
Notes: Making sure your surveyor can be as simple as a statement in a Request for Proposal or Bid with a statement stating such. Maybe

## Slide 8: Why state licensure?
State Licensure - Terry
  Kansas (cont)
    (C) locating, relocating, establishing, re-establishing or retracing property lines or boundaries of any tract of land, road, right-of way or easement;
    (D) preparing the original descriptions of real property for the conveyance of or recording thereof and the preparation of graphics, data, maps, plans, reports, land subdivision plats, descriptions and projects that represent these surveys;
    (E) determining, by the use of principles of surveying, the position for any survey monument, whether boundary or nonboundary, or reference point and establishing or replacing any such monument or reference point;
    (F) making any survey for the division, subdivision or consolidation of any tract of land;
    (G) locating or laying out alignments, positions or elevations where such work is part of the construction of engineering or architectural works; and
    (H) creating, preparing or modifying electronic, computerized or other data relative to performance of the activities
Notes: Making sure your surveyor can be as simple as a statement in a Request for Proposal or Bid with a statement stating such. Maybe

## Slide 9: Why state licensure?
State Licensure - Terry
  New Mexico
    "surveying", "practice of surveying" or "surveying practice" means any service or work, the substantial performance of which involves the application of the principles of mathematics and the related physical and applied sciences for:
    (1) the measuring and locating of lines, angles, elevations and natural and man-made features in the air, on the surface of the earth, within underground workings and on the beds or bodies of water for the purpose of defining location, areas and volumes;
    (2) the monumenting of property boundaries and for the platting and layout of lands and subdivisions;
    (3) the application of photogrammetric methods used to derive topographic and other data;
Notes: Making sure your surveyor can be as simple as a statement in a Request for Proposal or Bid with a statement stating such. Maybe

## Slide 10: Why state licensure?
State Licensure - Terry
  New Mexico (cont)
    (4) the establishment of horizontal and vertical controls that will be the basis for all geospatial data used for future design surveys, including construction staking surveys, surveys to lay out horizontal and vertical alignments, topographic surveys, control surveys for aerial photography for the collection of topographic and planimetric data using photogrammetric methods and construction surveys of engineering and architectural public works projects;
    (5) the preparation and perpetuation of maps, records, plats, field notes, easements and property descriptions; and
    (6) the depiction and transmittal by paper or digital means of any digital geospatial data for use in geographic information systems or land information systems that purports to be the authoritative location of points or features of a survey regulated by the Engineering and Surveying Practice Act,
    but excludes data used solely for a cadastre, such as assessment and tax mapping purposes, or general representations of surveyed or historic data used for mapping purposes, such as land parcels and built infrastructure;
Notes: Making sure your surveyor can be as simple as a statement in a Request for Proposal or Bid with a statement stating such. Maybe

## Slide 11: Why state licensure?
State Licensure - Terry
  Virginia
    The "practice of land surveying" includes surveying of areas for a determination or correction, a description, the establishment or reestablishment of internal and external land boundaries, or the determination of topography, contours or location of physical improvements, and also includes the planning of land and subdivisions thereof.
    The term "planning of land and subdivisions thereof" shall include, but not be limited to, the preparation of incidental plans and profiles for roads, streets and sidewalks, grading, drainage on the surface, culverts and erosion control measures, with reference to existing state or local standards.
Notes: Making sure your surveyor can be as simple as a statement in a Request for Proposal or Bid with a statement stating such. Maybe

## Slide 12: Why state licensure?
Examples of Discipline –
  Bob, PE/PLS The Board received a complaint alleging Bob produced a survey that did not comply with the standards of practice for surveying in Alabama. Bob agreed to a consent order that required him to pay a $1,500 fine to the Board, his Professional Land Surveyor license be suspended for two years (with that suspension stayed) and to provide to the Board, upon request, a list of the surveying jobs performed within a one month period during the stayed suspension period to be reviewed for compliance with the standards of practice. The Consent Order and Final Order would be a public record.
Notes: Making sure your surveyor can be as simple as a statement in a Request for Proposal or Bid with a statement stating such. Maybe

## Slide 13: PREqualifying your surveyor
Execution Plan
  Why is it important?
    By asking a contractor for an execution plan it will provide you a measure in determining whether or not the company has the knowledge and adequate and experienced staff to complete the work on time and as expected.
  What should you ask for?
    A plan will demonstrate the work is expected to be completed based on the parameters (schedule) you provide.
    Crew size and number
    Location of Key Personnel
    Resumes of Key Personnel
    Standards to be used

## Slide 14: PREqualifying your surveyor
Safe Work Plan
  Why is it important?
    By asking for a Safe Work Plan before work begins, it will help you ensure the contractor has reviewed the project site and has worked to minimize the risks associated with the project.
  What is in it?
    Safety Manual or reference to a safety protocol
    Description of Tailgate Meetings
    Preliminary Hazard Identification
    Recognition of injury protocol
    List of hospital, emergency rooms, and other important places with contact information
  Which is safer?
    2-man crew vs. 1-man crew

## Slide 15: ESTIMATING A PROJECT

## Slide 16: What is GIS?
Using a Geographic Information System (GIS) is a great tool which assists stakeholders in determining completion dates and evaluate progress.
Pros
  It is getting more accurate and is a great way to proof the proposed route with overlays of property and environmental data in a desktop environment.
  It can be used quickly to produce preliminary exhibits using appraisal district or other vendor data.
  In some states, these exhibits can be used for ROW agents to discuss the project with landowner and even submitted as an exhibit to the easement agreement.
Cons
  Relying solely on these exhibits may create problems later in the project. They are not surveyed on the ground and actual easement could vary after survey complete.
  Some states, GIS is considered surveying.
Notes: GIS
A new buzzword.
Get It Surveyed
Pros
Appraisal District data is not always correct.
Enables the surveyor to provide preliminary exhibits quickly which assists the ROW group in getting survey permissions quicker.
Cons
Landowner might construe it as a “surveyed” product and that might cause issues with State Board.
Since it is not surveyed on the ground, it may not show an accurate picture of where the boundary is.

## Slide 17: Estimating a project
To create an even response to your RFP, provide the surveyor with:
  Safety and Access Requirements
  Location of Route / Site to be surveyed
  Scope of Work
    As the operator, should I have my scope of work or rely on the surveyor to provide one?
  Survey Standards
    What is required when staking centerline.
      Leave stakes in the ground?
      Tree cutting and crops
  Expected deliverables and schedule
    Alignment sheets, Parcel Sketches, Permit Exhibits
    Blue Sky, Skyline, AutoCAD, MicroStation, GIS Database
  Construction schedule.

## Slide 18: Factors which affect price and performance
Length of route
Number of parcels
  Parcel congestion
  City vs. Rural
Boundary monumentation (PLSS)
Number of Permits
    What is the additional area required to be surveyed for the crossing?
    DOT standards, FEMA standards, State, County, City
Per diem expected or not?
    Working in Permian, the Bakken, or other high priced area?

## Slide 19: Factors which affect price and performance (CONT)
  Terrain
    No GPS
      Lots of hills
      Lots of trees
Schedule
  Survey Permissions Complete
  Working Schedule – 5-day, 6-day, 7-day?
  Construction Duration
    The surveyor is at the mercy of the contractor and needs to be onsite to obtain critical as-built data.
    Don’t trust your contractor to get the data needed.
    Use a 3rd party or your surveyor

## Slide 20: Factors which affect price and performance (CONT)
Scope of Work
  What is the work you want your surveyor to do?
  I just want plats!
  Yes, but the project may require any or all of the below…
    Project Specifications and Requirements
    Survey Control
    Preliminary Survey, Design Survey, Topographic Survey
    Boundary Survey, (uncertainty of PLSS monumentation)
    Mapping / Plats / Exhibits
    Alignment Sheets
    Construction Staking
    As-Built Survey (Pipeline)
    Drone / sUAS / LiDAR
    Aerial Imagery

## Slide 21: CONTRACTING

## Slide 22: CONTRACTING PROCESS
Contracting Process
  RFP – Request for Proposal
    Offeror is expecting pricing
  RFQ – Request for Qualification
    Offeror is not expecting pricing.
    Qualification based selection only.
    In some states, RFQ is required by state statute for all government work
  RFI – Request for Information
    Offeror wants to determine who the possible bidders of the work are, but there is not a project defined.
  How do you handle surveyors assumptions on a project?
    Each assumption is a risk to your project the surveyor has identified.
    How are you mitigating these risk?
  Always include Submittal Timelines and Deadline for Questions

## Slide 23: CONTRACT TYPES
Fee Types
  Time and Materials (T&M)
    Used when a project cost will be uncertain but there is enough faith in the contractor to manage and report the cost on a regular basis.
    Offeror Risk = HIGH; Contractor Risk = LOW
  Time and Material, Not-to-Exceed (T&M, NTE)
    Used when project cost will be uncertain but there is a requirement to cap the budget at a certain amount.
    Offeror Risk = MEDIUM; Contractor Risk = MEDIUM
  Lump Sum, NTE (LS)
    Used when a project cost is undefined but the offeror wants to mitigate their risk by pushing it to the contactor.
    - Offeror Risk = LOW; Contractor Risk = HIGH

## Slide 24: CREATE contractor EXPECTATIONS
Kickoff Meeting
  One for every project, large or small
  Provide a Written Agenda
  Spell out project expectations
Change Order Process
  Have a written change order process
  Define who can identify and who can authorize.
Communication Plan
  Include and maintain all stakeholders
  Include and maintain an authority matrix
    Can field personnel authorize additional work?
  Include best method of communication
  Who to notify in case of emergency

## Slide 25: Keep your contractor in line
Corrective Measures
  When do they apply?
    Define internally the process for identifying potential project pitfalls
  How is an issue elevated to a Senior Manager or other personnel?
    Define internally the process for when an issue has become too large to be handled by project personnel.
How to monitor
  Create a metric for understanding progress from the execution plan. If the surveyor says they will get a mile a day, why are they not.
    Miles surveyed, Tracts surveyed, etc
  Weekly Reporting
    Ask for an issues log or some other weekly report qualifying issues related to the project and what has been unexpected or under estimated.
    Ask for financial and deliverable progress along with expected milestone dates

## Slide 26: Questions?
Questions?
Important for the success of your project
  Prequalify your contractor
  Provide an accurate RFP to your potential contractor
  Managing the contractor relationship and expectations

## Slide 27: Closing thoughts